## Product Backlog
Product Backlog | Sprint | Difficulty | Hours
User launches program and sees a title/introduction screen/message | 1 | Easy | 1
Allow user to select a timed game or non-timed game |  |  | 0
Create 9x5 board | 1 | Easy | 1
*Change board size |  |  | 0
Make sure initial game board is valid | 1 | Easy | 1
Draw pieces | 1 | Easy | 1
Create button/function to start and restart game | 1 | Mid | 2
User input box | 1 | Easy | 1
User enters a move by inputting board positions | 1 | Mid | 2
User enters a move by defined click-and-move process |  |  | 0
Maintain board state |  |  | 0
User sees a display of the current board state |  |  | 0
Track whose turn it is | 1 | Easy | 1
Display whose turn it is | 1 | Easy | 1
Check to see if both players still have pieces. |  |  | 0
Keep track of pieces that are gone |  |  | 0
Display removed pieces on the side of the board |  |  | 0
Check to see if player has any moves to perform. If they don’t, they lose |  |  | 0
Check if maximum number of moves has been reached. | 1 | Mid | 2
User gets response of invalid if proposing an invalid move |  |  | 0
Computer identifies all valid moves |  |  | 0
Computer can randomly select a valid move | 1 | Mid | 2
Board evaluation function determines winner/loser | 1 | Easy | 1
Highlight the pieces that have valid moves available |  |  | 0
*Show all valid moves for a selected piece |  |  | 0
Only allow users to effect pieces they control |  |  | 0
Allow diagonal and forward movement | 1 | Hard | 4
Disallow pieces to move to a spot with a piece in it | 1 | Mid | 2
Track where pieces have been, they are not allows to be in the same space |  |  | 0
Track multiple jumps |  |  | 0
Captures 2 different ways | 1 | Hard | 4
If a capture move can be made, it must be made |  |  | 0
Allow to move only if cannot capture | 1 | Hard | 4
Allow user to pass turn |  |  | 0
*Allow user to undo a move |  |  | 0
Min/max tree used for AI |  |  | 0
Computer looks ahead one move in tree |  |  | 0
Alpha-beta pruning implemented at one level |  |  | 0
Alpha-beta pruning implemented across all levels |  |  | 0
Iterative deepening implemented |  |  | 0
Make a board that can be accessed remotely |  |  | 0
Make an AI that can be played against remotely |  |  | 0
Timer for AI |  |  | 0
Timer for User |  |  | 0
Visual for AI’s last move |  |  | 0
Visual for user’s last move |  |  | 0
Display count down timer |  |  | 0
Program AI with staggles |  |  | 0
Difficulty settings on the AI |  |  | 0
Make funny names for the AI difficulty settings |  |  | 0
*Make a chat function |  |  | 0
*Make AI taunt in chat |  |  | 0
30

## Sprint 1
Sprint 1 Backlog | Difficulty | Hours | Date | 2013-03-05 | 2013-03-06
User launches program and sees a title/introduction screen/message – Easy | Easy | 1 |  | Initial | SCRUM 1 | SCRUM 2 | SCRUM 3
Create 9x5 board – Easy | Easy | 1 | Sprint 1 | 30
Make sure initial game board is valid – Easy | Easy | 1 |  |  |  |  | 30
Draw pieces – Easy | Easy | 1
Create button/function to start and restart game – Mid | Mid | 2
User input box – Easy | Easy | 1
User enters a move by inputting board positions – Mid | Mid | 2
Track whose turn it is – Easy | Easy | 1
Display whose turn it is – Easy | Easy | 1
Check if maximum number of moves has been reached – Mid | Mid | 2
Computer can randomly select a valid move – Mid | Mid | 2
Board evaluation function determines winner/loser – Easy | Easy | 1
Allow diagonal and forward movement – Hard | Hard | 4
Disallow pieces to move to a spot with a piece in it – Mid | Mid | 2
Captures 2 different ways – Hard | Hard | 4
Allow to move only if cannot capture – Hard | Hard | 4
| Total Hours | 30

## Sprint 2
Sprint 2 Backlog | Difficulty | Hours | Date
|  | 0 |  | Initial | SCRUM 1 | SCRUM 2 | SCRUM 3
|  | 0 | Sprint 2 | 0
|  | 0 |  |  |  |  | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
| Total Hours | 0

## Sprint 3
Sprint 3 Backlog | Difficulty | Hours | Date
|  | 0 |  | Initial | SCRUM 1 | SCRUM 2 | SCRUM 3
|  | 0 | Sprint 2 | 0
|  | 0 |  |  |  |  | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
| Total Hours | 0